## READ ME
Upgrading from classic Outlook to new Outlook for Windows
Sample Pilot Test Plan
A successful pilot validates how new Outlook will be used on a daily basis, by your end-users. This means understanding who your users are, how they communicate and collaborate and what features will help optimize their productivity. When upgrading from classic Outlook, you'll want to validate the core communication functionality around mail, calendar, contacts, as applicable.
Your pilot test plan should verify "real-world" productivity use cases in conjunction with the available features in new Outlook for Windows. This plan allows users to enter tasks, indicate that they have completed the requested task, and capture top-of-mind feedback as they progress through the testing. This plan is designed to accommodate 30-minutes of a user's time each week. Depending on the duration of your pilot, you may opt to consolidate.
How to use this Test Plan:
- Personalize your test scenarios and features for your pilot users (personas) as needed
- Share this plan with your pilot users in this Excel format or transpose to a format you prefer, to more easily capture user sentiment (eg an online survey form) as part of your communications.
​© 2024 Microsoft Corporation. All rights reserved. Materials available at this web page are provided "as-is." Information and views expressed at this page and in these materials, including URL and other internet website references, may change without notice. You bear the risk of using them.
This page and these materials do not provide you with any legal rights to any intellectual property in any Microsoft product. Microsoft customers and partners may copy, use and share these templates to assist with their new Outlook upgrade planning and implementation.

## MAIL
USING EMAIL
Sample use case: Enter scenario and supporting actions here. Sample actions have been provided.
Test | Test Steps | Test Completed? | Initial experience? | Notes and Feedback
Customize your views by changing your ribbon, folder pan, and density settings | In the simplified ribbon, explore the layout and density settings
In the classic ribbon, explore the layout and density settings
Create a rule to help handle incoming messages | In the simplified ribbon, go to "View Settings"
Go to "Mail", then "Rules"
Create a Rule !
Add more tests that users in your organization can use to explore...
`

## CALENDAR
USING THE CALENDAR
Sample use case: Enter scenario and supporting actions here. Sample actions have been provided.
Test | Test Steps | Test Completed? | Initial experience? | Notes and Feedback
Schedule a Teams meeting from Outlook | Open a New Event
Enter meeting details
Toggle "Teams Meeting" to on!
Update your work hours and location | In the simplified ribbon, go to "View Settings"
Go to "Calendar", then select "Work hours and location"
Change your working hours!
Add more tests that users in your organization can use to explore...

## CONTACTS
USING CONTACTS
Sample use case: Enter scenario and supporting actions here. Sample actions have been provided.
Test | Test Steps | Test Completed? | Initial experience? | Notes and Feedback
Create a contact list | Go to the Contacts module on the left navigation pane
Click on the downward pointing arrow on the "New Contact" button on the top left of the screen...
Select new contact list.
Enter the details, and click "Create"
Add a favorite | Go to the Contacts module on the left navigation pane
Click on "Your contacts" in the list on the left
Select a contact
Select "Add to favorites" from the menu
Your selected contact is now a favorite!
Add more tests that users in your organization can use to explore...

## Version history (hidden)
Version | Changes | Date
2.0 | Initial Release | 2017-08-10